# atlas week 34

Weekly status report

| Project ID | NA |
| --- | --- |
| Project Name | Atlas |
| Start Date | — |
| End Date | — |
| Status | At Risk |

## Executive Summary

Atlas remains amber at week 34. The migration dry run completed in 4hrs 20 against a 6-hour plan, with 2 accounts failing to reconcile. The blocker is Northgate: the API spec requested 3 weeks ago has still not arrived, and if it is not received by the 19th the October window is lost and the work moves to January because of the freeze.

## Key Decisions

None.

## Key Accomplishments

- Migration dry run completed on Saturday in 4hrs 20 vs the 6 hours planned

## Upcoming Activities

- Ken to investigate the 2 accounts that didn't reconcile — probably the fx rounding thing again

- Check the budget position with Javier (40k over on contractors, under on licences)

- Sofia covering standups while Priya is out from the 12th for 2 weeks

## Key Risks / Challenges

| Risk / Challenge | Impact | Raised | Owner | Mitigation | Expected closure |
| --- | --- | --- | --- | --- | --- |
| Northgate API spec 3 weeks overdue | If we don't have it by the 19th the October window is gone and we're into January because of the freeze | — | Marcus Webb | Chased twice; no date given | the 19th |
| 2 accounts didn't reconcile in the dry run | — | — | Ken Osei | Ken looking, probably the fx rounding thing again | — |

Internal