## Slide 1
atlas week 34
Project ID | Project Name | Start Date | End Date | Status
NA | Atlas | — | — | At Risk
Executive Summary
Atlas remains amber at week 34. The migration dry run completed in 4hrs 20 against a 6-hour plan, with 2 accounts failing to reconcile. The blocker is Northgate: the API spec requested 3 weeks ago has still not arrived, and if it is not received by the 19th the October window is lost and the work moves to January because of the freeze.
Key Decisions
None
Key Accomplishments
Migration dry run completed on Saturday in 4hrs 20 vs the 6 hours planned
Upcoming Activities
Ken to investigate the 2 accounts that didn't reconcile — probably the fx rounding thing again
Check the budget position with Javier (40k over on contractors, under on licences)
Sofia covering standups while Priya is out from the 12th for 2 weeks
Key Risks / Challenges
Risk / Challenge | Impact | Raised | Owner | Mitigation | Expected closure
Northgate API spec 3 weeks overdue | If we don't have it by the 19th the October window is gone and we're into January because of the freeze | — | Marcus Webb | Chased twice; no date given | the 19th
Internal
Not Started
On Track
In Progress
At Risk
Delayed
Completed
Closed

## Slide 2
atlas week 34 — Key Risks / Challenges (continued)
Key Risks / Challenges
Risk / Challenge | Impact | Raised | Owner | Mitigation | Expected closure
2 accounts didn't reconcile in the dry run | — | — | Ken Osei | Ken looking, probably the fx rounding thing again | —
atlas week 34